## Vulnerability Register
VULNERABILITY MANAGEMENT REGISTER
Track every vulnerability from discovery through remediation. One row per finding.
Vuln ID | Scan Date | Asset / Host | CVE | Vulnerability | Severity | CVSS Score | Remediation | Owner | SLA Due Date | Status | Date Closed
VLN-001 | 2025-04-01 | 192.168.1.10 | CVE-2021-44228 | Apache Log4j RCE (Log4Shell) | Critical | 10.0 | Update Log4j to 2.17.1. Apply WAF rules immediately. | IT Security | 2025-04-08 | Open
VLN-002 | 2025-04-01 | 192.168.1.10 | CVE-2021-34527 | Windows Print Spooler RCE (PrintNightmare) | Critical | 8.8 | Apply KB5004945. Disable Print Spooler if not required. | IT Operations | 2025-04-08 | In Progress
VLN-003 | 2025-04-01 | 192.168.1.25 | CVE-2022-26134 | Atlassian Confluence OGNL Injection | Critical | 9.8 | Upgrade Confluence to 7.4.17 immediately. | DevOps | 2025-04-08 | Remediated | 2025-04-03
VLN-004 | 2025-04-01 | 192.168.1.15 | CVE-2023-23397 | Microsoft Outlook Privilege Escalation | High | 9.8 | Apply March 2023 Microsoft security update. | IT Operations | 2025-04-15 | Open
VLN-005 | 2025-04-01 | 192.168.1.20 | CVE-2021-26855 | Exchange Server SSRF (ProxyLogon) | High | 9.1 | Apply KB5000871. Migrate to Exchange Online if possible. | IT Operations | 2025-04-15 | In Progress
VLN-006 | 2025-04-01 | 192.168.1.30 | CVE-2022-22965 | Spring Framework RCE (Spring4Shell) | High | 9.8 | Update Spring Framework to 5.3.18 or 5.2.20. | DevOps | 2025-04-15 | Open
VLN-007 | 2025-04-01 | 192.168.1.10 | CVE-2019-0708 | Windows RDS RCE (BlueKeep) | High | 9.8 | Apply KB4499175. Disable RDP if not required. | IT Operations | 2025-04-15 | Remediated | 2025-04-02
VLN-008 | 2025-04-01 | 192.168.1.40 | CVE-2021-21985 | VMware vCenter RCE | High | 9.8 | Update vCenter to 6.7 U3n or 7.0 U2b. | Infrastructure | 2025-04-15 | Open
VLN-009 | 2025-04-01 | 192.168.1.15 | CVE-2020-1472 | Netlogon Elevation of Privilege (Zerologon) | High | 10.0 | Apply August 2020 update. Enable enforcement mode. | IT Operations | 2025-04-15 | Remediated | 2025-04-04
VLN-010 | 2025-04-01 | 192.168.1.50 | CVE-2021-26084 | Atlassian Confluence OGNL Injection | Medium | 9.8 | Upgrade Confluence to 7.13.0 or apply workaround. | DevOps | 2025-05-01 | Open
VLN-011 | 2025-04-01 | 192.168.1.55 | CVE-2022-0847 | Linux Kernel Privilege Escalation (Dirty Pipe) | Medium | 7.8 | Update kernel to 5.16.11 or later. | Infrastructure | 2025-05-01 | In Progress
VLN-012 | 2025-04-01 | 192.168.1.60 | CVE-2021-3156 | Sudo Heap Buffer Overflow (Baron Samedit) | Medium | 7.8 | Update sudo to 1.9.5p2 or later. | Infrastructure | 2025-05-01 | Open
VLN-013 | 2025-04-01 | 192.168.1.25 | CVE-2020-0601 | Windows CryptoAPI Spoofing | Medium | 8.1 | Apply January 2020 security update. | IT Operations | 2025-05-01 | Remediated | 2025-04-05
VLN-014 | 2025-04-01 | 192.168.1.70 | CVE-2019-11043 | PHP-FPM RCE | Low | 9.8 | Update PHP to 7.1.33 or later. | DevOps | 2025-06-01 | Accepted
VLN-015 | 2025-04-01 | 192.168.1.80 | CVE-2020-8597 | PPP Daemon Buffer Overflow | Low | 9.8 | Update pppd to 2.4.8 or later. | Infrastructure | 2025-06-01 | Open

## SLA Policy
VULNERABILITY MANAGEMENT SLA POLICY
Defines remediation timeframes by severity. Apply consistently across all findings.
Severity | CVSS Range | Remediation SLA | Required Action | Escalation | Examples
Critical | 9.0–10.0 | 24–48 hours | Immediate containment. Emergency patch or compensating control within 24hrs. CISO notified. | Escalate to CISO and leadership immediately. Incident response may apply. | Log4Shell, ProxyLogon, EternalBlue
High | 7.0–8.9 | 7–14 days | Patch within SLA. Compensating controls if patch unavailable. Weekly progress update. | Escalate to security manager if not resolved within 7 days. | PrintNightmare, Zerologon, Spring4Shell
Medium | 4.0–6.9 | 30 days | Patch within 30 days. Track in vulnerability register. Include in monthly report. | Escalate to IT manager if not resolved within 30 days. | Dirty Pipe, Baron Samedit, CryptoAPI
Low | 0.1–3.9 | 90 days | Patch within 90 days or accept risk formally. Document decision. | Review at quarterly vulnerability management meeting. | Minor config issues, outdated non-critical software
Info | N/A | Best effort | Informational only. No remediation required. Review and document. | No escalation required. | Open ports, banners, version disclosure

## Dashboard
VULNERABILITY MANAGEMENT DASHBOARD
Executive summary — update after every scan cycle.
CURRENT SCAN SUMMARY
Total vulnerabilities | Critical open | High open | Medium open | Low open | Remediated | Overdue
14 | 1 | 3 | 2 | 1 | 4 | 0
SEVERITY BREAKDOWN BY STATUS
Severity | Total | Open | In Progress | Remediated | Accepted | False Positive | % Remediated
Critical | 3 | 1 | 1 | 1 | 0 | 0 | 33%
High | 6 | 3 | 1 | 2 | 0 | 0 | 17%
Medium | 4 | 2 | 1 | 1 | 0 | 0 | 25%
Low | 2 | 1 | 0 | 0 | 1 | 0 | 0%
Info | 0 | 0 | 0 | 0 | 0 | 0
SCAN HISTORY & TREND
Scan Date | Critical | High | Medium | Low | Info | Total | Notes
2025-01-01 | 5 | 12 | 23 | 8 | 14 | 62 | Baseline scan
2025-02-01 | 3 | 9 | 20 | 7 | 14 | 53 | Post-patch cycle 1
2025-03-01 | 3 | 8 | 18 | 6 | 14 | 49 | Post-patch cycle 2
2025-04-01 | 3 | 5 | 4 | 2 | 1 | 15 | Current scan

## Asset Inventory
ASSET INVENTORY — SCAN SCOPE
Define which assets are in scope for vulnerability scanning. Review quarterly.
Asset ID | Hostname / IP | Asset Type | OS / Platform | Business Owner | Environment | Criticality | Last Scanned
AST-001 | 192.168.1.10 | Server | Windows Server 2019 | IT Operations | Production | Critical | 2025-04-01
AST-002 | 192.168.1.15 | Server | Windows Server 2016 | IT Operations | Production | Critical | 2025-04-01
AST-003 | 192.168.1.20 | Server | Windows Server 2019 | IT Operations | Production | High | 2025-04-01
AST-004 | 192.168.1.25 | Server | Ubuntu 20.04 LTS | DevOps | Production | Critical | 2025-04-01
AST-005 | 192.168.1.30 | Server | CentOS 7 | DevOps | Production | High | 2025-04-01
AST-006 | 192.168.1.40 | Virtual | VMware ESXi 7.0 | Infrastructure | Production | Critical | 2025-04-01
AST-007 | 192.168.1.50 | Server | Ubuntu 18.04 LTS | DevOps | Staging | Medium | 2025-04-01
AST-008 | 192.168.1.55 | Server | Debian 10 | Infrastructure | Production | High | 2025-04-01
AST-009 | 192.168.1.60 | Server | Ubuntu 20.04 LTS | DevOps | Production | Medium | 2025-04-01
AST-010 | 192.168.1.70 | Server | CentOS 8 | DevOps | Production | Medium | 2025-04-01
AST-011 | 192.168.1.80 | Network | Linux (pppd) | Infrastructure | Production | Low | 2025-04-01

## Remediation Tracker
REMEDIATION ACTION TRACKER
Track every remediation action with owner, deadline, and evidence of fix.
Action ID | Vuln ID | Asset | Action Required | Owner | Priority | Due Date | Status | Evidence / Notes
REM-001 | VLN-001 | 192.168.1.10 | Update Log4j to 2.17.1. Apply WAF blocking rules immediately. | IT Security | Critical | 2025-04-08 | Open
REM-002 | VLN-002 | 192.168.1.10 | Apply KB5004945. Restart Print Spooler service after patch. | IT Operations | Critical | 2025-04-08 | In Progress | Patch downloaded, testing in staging
REM-003 | VLN-003 | 192.168.1.25 | Upgrade Confluence to 7.4.17. Verified in staging first. | DevOps | Critical | 2025-04-08 | Complete | Upgraded April 3. Scan confirmed clean.
REM-004 | VLN-004 | 192.168.1.15 | Apply March 2023 Outlook update via WSUS. | IT Operations | High | 2025-04-15 | Open
REM-005 | VLN-005 | 192.168.1.20 | Apply KB5000871. Run EOMT.ps1 script post-patch. | IT Operations | High | 2025-04-15 | In Progress | EOMT script run. Patch scheduled weekend.
REM-006 | VLN-007 | 192.168.1.10 | Apply KB4499175. Disable RDP on non-management hosts. | IT Operations | High | 2025-04-15 | Complete | Patched April 2. RDP disabled on 3 hosts.
REM-007 | VLN-009 | 192.168.1.15 | Apply August 2020 Netlogon patch. Enable enforcement mode. | IT Operations | High | 2025-04-15 | Complete | Patched April 4. Enforcement mode enabled.
REM-008 | VLN-010 | 192.168.1.50 | Upgrade Confluence to 7.13.0 or apply workaround script. | DevOps | Medium | 2025-05-01 | Open
REM-009 | VLN-014 | 192.168.1.70 | Risk accepted — host isolated, no internet exposure. | DevOps | Low | 2025-06-01 | Accepted | Risk acceptance signed by IT Manager 2025-04-01

## Remediation Decision Tree
VULNERABILITY REMEDIATION DECISION TREE
Follow this decision tree for every vulnerability. Every finding must result in: Patch · Compensating Control · Risk Acceptance
STEP 1 — TRIAGE
As soon as a vulnerability is discovered, answer these questions before deciding on a remediation path.
# | Question / Factor | How to assess | If YES / Action | If NO / Alternative
Q1 | Is this a false positive? | Review the finding and cross-reference with the CVE database. | False positive → mark as False Positive. Document evidence. No further action. | Confirmed → proceed to Step 2
Q2 | What is the CVSS score? | Use CVSS as your starting severity. Critical ≥9.0 · High 7.0–8.9 · Medium 4.0–6.9 · Low <4.0 | Sets your SLA clock. Critical: 48hrs · High: 14 days · Medium: 30 days · Low: 90 days | Proceed to Step 3
Q3 | Is the asset internet-facing? | Internet-facing assets with exploitable vulns are highest priority — attackers can reach them directly. | Internet-facing + Critical/High → escalate immediately. Treat as P1. | Internal only → follow standard SLA
STEP 2 — PRIORITISATION
CVSS score alone is not enough. Apply these risk context factors to determine true priority.
# | Question / Factor | How to assess | If YES / Action | If NO / Alternative
F1 | Known exploit in the wild? | Check CISA KEV catalog and NVD. If exploited in wild, treat as one severity higher. | In CISA KEV → treat as Critical regardless of CVSS score. | No known exploit → use CVSS score
F2 | What data does the asset hold? | An asset holding PII, PCI, or PHI has higher effective risk than one holding internal data only. | Sensitive data asset → increase priority by one level. | Non-sensitive → standard priority
F3 | What is the blast radius? | Can the attacker pivot to other systems? Domain controllers and core infra have maximum blast radius. | High blast radius → escalate to CISO. Include in IR planning. | Isolated system → standard process
STEP 3 — REMEDIATION PATH
Every vulnerability must be assigned one of three remediation paths. Document the decision.
# | Question / Factor | How to assess | If YES / Action | If NO / Alternative
PATH A | Can a patch be applied? | Check vendor advisory. Verify patch is tested and approved for your environment. | Patch available + approved → PATCH. Schedule within SLA. Test in staging first. | No patch available → go to Path B
PATH B | Can a compensating control be applied? | If patching is not possible, apply a control that reduces exploitability or impact. | WAF rule, network segmentation, disable service, restrict access, enforce MFA. | No compensating control possible → go to Path C
PATH C | Can the risk be formally accepted? | Valid only when patching and compensating controls are genuinely not feasible. | Written justification + business owner sign-off + CISO approval + review date. | Escalate — do not leave unaddressed
STEP 4 — VERIFICATION
Remediation is not complete until a re-scan confirms the vulnerability is gone.
# | Question / Factor | How to assess | If YES / Action | If NO / Alternative
V1 | Re-scan the affected asset | Run a targeted Nessus scan against the specific host after remediation. | Vulnerability gone → mark Remediated. Record date closed and evidence. | Vulnerability still present → remediation failed. Restart process.
V2 | Verify compensating control | For compensating controls, test the control actually mitigates the risk. | Control effective → document test evidence. Mark status Remediated with note. | Control not effective → escalate and find alternative.
V3 | Update the register | Every closure must be recorded with date closed and evidence. Auditors will ask. | Required: re-scan result, patch ticket number, or compensating control test result. | Missing evidence → finding remains Open for audit purposes.

## Patch Management Log
PATCH MANAGEMENT LOG
Record every patch applied. Evidence required for SOC 2 CC6.7 and ISO 27001 A.8.8.
Patch ID | Vuln ID | Asset / Host | CVE / KB | Patch / Fix | Patch Source | Tested in Staging | Applied By | Date Applied | Re-scan Result | Evidence
PCH-001 | VLN-003 | 192.168.1.25 | CVE-2022-26134 | Upgrade Confluence to 7.4.17 | Atlassian Advisory | Yes | Victor E. | 2025-04-03 | Clean | JIRA-1234 · Re-scan 2025-04-03
PCH-002 | VLN-007 | 192.168.1.10 | CVE-2019-0708 / KB4499175 | Windows Security Update KB4499175 | Microsoft Update Catalog | Yes | IT Operations | 2025-04-02 | Clean | JIRA-1201 · Re-scan 2025-04-02
PCH-003 | VLN-009 | 192.168.1.15 | CVE-2020-1472 / KB4571694 | Netlogon patch + enforcement mode | Microsoft Update Catalog | Yes | IT Operations | 2025-04-04 | Clean | JIRA-1218 · Re-scan 2025-04-04
PCH-004 | VLN-013 | 192.168.1.25 | CVE-2020-0601 / KB4528760 | Windows CryptoAPI patch KB4528760 | Microsoft Update Catalog | Yes | IT Operations | 2025-04-05 | Clean | JIRA-1225 · Re-scan 2025-04-05

## Compensating Controls
COMPENSATING CONTROLS REGISTER
Applied when a patch is unavailable. Must be reviewed at every scan cycle.
Control ID | Vuln ID | Asset | Vulnerability | Control Applied | Control Type | Implemented By | Date Applied | Review Date | Effectiveness
CC-001 | VLN-001 | 192.168.1.10 | Apache Log4Shell (CVE-2021-44228) | WAF rule blocking JNDI lookup patterns. Log4j update scheduled next maintenance window. | WAF Rule | IT Security | 2025-04-01 | 2025-04-08 | Effective — JNDI patterns blocked
CC-002 | VLN-005 | 192.168.1.20 | Exchange ProxyLogon (CVE-2021-26855) | EOMT.ps1 script applied. Exchange isolated to internal VLAN. External access disabled. | Network Segmentation | IT Operations | 2025-04-02 | 2025-04-15 | Effective — external access removed
CC-003 | VLN-008 | 192.168.1.40 | VMware vCenter RCE (CVE-2021-21985) | vCenter restricted to admin VLAN only. External access removed via firewall rule. | Access Restriction | Infrastructure | 2025-04-03 | 2025-04-15 | Effective — access restricted to 3 admin IPs

## Risk Acceptance Register
RISK ACCEPTANCE REGISTER
Risk acceptance is a last resort — not a default. Every entry requires business owner and CISO sign-off.
Risk ID | Vuln ID | Asset | Vulnerability | Severity | Justification | Business Owner | CISO Approval | Accepted Date | Review Date
RA-001 | VLN-014 | 192.168.1.70 | PHP-FPM RCE (CVE-2019-11043) | Low | Host is isolated — no internet exposure, no sensitive data. Patch requires PHP upgrade breaking legacy app. Reviewed by IT Manager. | IT Manager — J. Smith | CISO Approved | 2025-04-01 | 2025-07-01
RISK ACCEPTANCE RULES
1. | Critical vulnerabilities cannot be risk accepted — they must be patched or have a compensating control applied.
2. | High vulnerabilities require CISO approval before risk acceptance. Business owner alone is not sufficient.
3. | All accepted risks must have a review date — maximum 90 days for High, 6 months for Medium and Low.
4. | Risk acceptance does not close the vulnerability — it remains Open in the register with status Accepted.
5. | At review date, the risk must be reassessed. If still unpatched, a new acceptance must be signed.
6. | Auditors will review this register. Every entry needs a documented justification and named approver.